# A. Project

Project title, acronym and reporting period are given. In case of changes, indicate these using another colour.

| Project title | Conservation and diversity in transcriptional regulation of developmental processes in crop and model plant species |
| --- | --- |
| Project acronym | CISCODE |
| Start date | 1 September 2007 |
| Reporting period | 1-18 month |
| Reporting date | February 2009 |

# B. Consortium

Partner details except for the research team are given. In case of changes, indicate these using another colour.

| Partner 1 (coordinator) |  |  |  |
| --- | --- | --- | --- |
| Name of grantholder | Prof. Gerco C. Angenent |  |  |
| Institution | Radboud Universiteit Nijmegen Fac. Natuurwetenschappen, Wiskunde en Informatica Experimental Botany |  |  |
| Address | Toernooiveld 1 6525 ED Nijmegen |  |  |
| Country | The Netherlands |  |  |
| Phone |  |  |  |
| E-mail | G.Angenent@science.ru.nl |  |  |
| Research team Staff members and students working on the project | Team leader / scientist / postdoc / technician / PhD student / MSc student / other : .. | Person months assigned to project | Is this team members appointed on project grant ? yes / no |
| Create extra rows if needed |  |  |  |

| Partner 2 |  |  |  |
| --- | --- | --- | --- |
| Name of grantholder | Prof. Yves van de Peer |  |  |
| Institution | Universiteit Gent Department of Plant Systems Biology Flanders Institute for Biotechnology (VIB) |  |  |
| Address | Technologiepark 927 9052 Gent |  |  |
| Country | Belgium |  |  |
| Phone |  |  |  |
| E-mail | yvpee@psb.ugent.be |  |  |
| Research team Staff members and students working on the project | Team leader / scientist / postdoc / technician / PhD student / MSc student / other : .. | Person months assigned to project | Is this team members appointed on project grant ? yes / no |
| Create extra rows if needed |  |  |  |

| Partner 3 |  |  |  |
| --- | --- | --- | --- |
| Name of grantholder | Dr. Jan Ulrich Lohrmann |  |  |
| Institution | Max-Planck-Institut für Entwicklungbiologie Abteilung Evolutionsbiologie |  |  |
| Address | Spemannstraße 37 D-72076 Tübingen |  |  |
| Country | Germany |  |  |
| Phone |  |  |  |
| E-mail | jlohmann@tuebingen.mpg.de |  |  |
| Research team Staff members and students working on the project | Team leader / scientist / postdoc / technician / PhD student / MSc student / other : .. | Person months assigned to project | Is this team members appointed on project grant ? yes / no |
| Create extra rows if needed |  |  |  |

| Partner 4 |  |  |  |
| --- | --- | --- | --- |
| Name of grantholder | Dr. Lucia Colombo |  |  |
| Institution | Università degli studi di Milano Dipartimento di Biologia |  |  |
| Address | Via Celoria 26 I-20133 Milano |  |  |
| Country | Italy |  |  |
| Phone |  |  |  |
| E-mail | lucia.colombo@unimi.it |  |  |
| Research team Staff members and students working on the project | Team leader / scientist / postdoc / technician / PhD student / MSc student / other : .. | Person months assigned to project | Is this team members appointed on project grant ? yes / no |
| Create extra rows if needed |  |  |  |

| Partner 5 |  |  |  |
| --- | --- | --- | --- |
| Name of grantholder | Dr. Giorgio Morelli |  |  |
| Institution | Institutio nazionale della nutrizione Unità di Nutrizione Sperimentale |  |  |
| Address | Via Ardcatina 546 I-00178 Roma |  |  |
| Country |  |  |  |
| Phone |  |  |  |
| E-mail |  |  |  |
| Research team Staff members and students working on the project | Team leader / scientist / postdoc / technician / PhD student / MSc student / other : .. | Person months assigned to project | Is this team members appointed on project grant ? yes / no |
| Create extra rows if needed |  |  |  |

| Partner 6 |  |  |  |
| --- | --- | --- | --- |
| Name of grantholder | Dr. Brendan H. Davies |  |  |
| Institution | University of Leeds Center for Plant Sciences Faculty of Biological Sciences |  |  |
| Address | LS2 9JT Leeds |  |  |
| Country | United Kingdom |  |  |
| Phone |  |  |  |
| E-mail | b.h.davies@leeds.ac.uk |  |  |
| Research team Staff members and students working on the project | Team leader / scientist / postdoc / technician / PhD student / MSc student / other : .. | Person months assigned to project | Is this team members appointed on project grant ? yes / no |
| Create extra rows if needed |  |  |  |

| Partner 7 |  |  |  |
| --- | --- | --- | --- |
| Name of grantholder | Dr. Robert Sablowski |  |  |
| Institution | John Innes Centre Department of Cellular and Developmental Biology |  |  |
| Address | Colney Lane Norwich NR4 7UH |  |  |
| Country | United Kingdom |  |  |
| Phone |  |  |  |
| E-mail | robert.sablowski@bbsrc.ac.uk |  |  |
| Research team Staff members and students working on the project | Team leader / scientist / postdoc / technician / PhD student / MSc student / other : .. | Person months assigned to project | Is this team members appointed on project grant ? yes / no |
| Create extra rows if needed |  |  |  |

# C. Project summary for public dissemination

Pse provide a summary of the project describing aim and current status of your project in 150-300 words for public dissemination. The summary will be published on the ERA-PG website and can be used for other websites (e.g. the sites of the national funding organisations) and within publications such as the mid-term report of the ERA-PG programme.

# D. Progress report

| D1. Achievement of planned objectives List the objectives and estimate the current degree of completion of the objectives. |  |  |
| --- | --- | --- |
| Deliverables and milestones | Degree of completion (partner involved) Done/on schedule/delayed/cancelled |  |
| M1.1: Target genes of key-regulators (Month 12) |  |  |
| D1.1 List of putative targets of FUL, RPL, REV (Month 12) |  |  |
| M1.2: ChIP-CHIP established (Month 12) |  |  |
| D1.2 List of putative targets for FUL, WUS, AG, STK, RPL, REV using ChIP (Month 18) |  |  |
| M1.3: Pipelines for identifying cis-regulatory elements established (Month 12) |  |  |
| D1.3: Compilation of cis-regulatory elements and regulatory modules for the transcription factor gene families of interest.(Month 12) |  |  |
| M1.4: Cis-trans interactions confirmed in vitro and in yeast (Month 24) |  |  |
| D1.4: List of confirmed interactions for at least 10 cis elements (Month 24) |  |  |
| M1.5: In vivo footprints established for the AG and RPL promoters and method available to other partners ( Month 18) |  |  |
| D1.5: List Cis-elements confirmed in vivo for at least 4 key promoters (Month 24) |  |  |
| M2.1: Isolated orthologous genes from 5 different species (Month 12) |  |  |
| D2.1: At least 10 orthologous genes (including upstream sequences) from 5 different species (Month 24) |  |  |
| M2.2: Established computational methods for the prediction of orthologous and paralogous cis-elements and determination of conservation and diversity (Month 18) |  |  |
| D2.2 Set of predicted orthologous and paralogous cis-elements for at least 10 different genes in the 6 species (Month 24) |  |  |
| M3.1: Expression patterns from reporter genes driven by promoter fragments available and stored in the central database (Month 30) |  |  |
| D3.1 Trangenic plants expressing 5 promoter-reporter constructs in each of the 6 species. (Month 30) |  |  |
| M3.2 Expression patterns of reporter genes driven by heterologous promoter fragments in Arabidopsis available and stored in the central database (Month 30) |  |  |
| D3.2 Expression patterns of at least 25 promoter-reporter constructs (5 constructs from each species) in Arabidopsis. (Month 30) |  |  |
| M3.3 Complementation assays with orthologous sequences in Arabidopsis (Month 36) |  |  |
| D3.3 Phenotypic analysis of sets of chimeric promoter-coding sequence constructs transformed into Arabidopsis mutants (Month 36) |  |  |
| M3.4: B. rapa TILLING population of approximately 5,000 M2 families available for screening (Month 24) |  |  |
| D3.4 Screening and isolation of lines from the B. rapa TILLING population with mutations in the Brassica orthologues of JAG, RPL, SHP1, and SHP2 and phenotypes characterised (Month 36) |  |  |

D2. Activities Describe the activities that have been performed to meet the objectives given in the proposal. Indicate for each activity the partners involved (PX, PY,..). For consortia with three or four partners this item should not exceed two pages. Larger consortia may use at maximum three pages.

WP1.1: Target gene identification by induced expression of transcription factors (P3, 1, 2, 4, 7). Please fill in max 10 lines per partner per WP where relevant……………….. WP1.2: Identification of direct targets by Chromatin Immuno Precipitation (ChIP) (P1, 2-7) ……………….. WP1.3: In silico prediction of cis-elements based on co-expression and conservation (P5, 7) ………………….. WP1.4: Confirmation of cis-sequence motifs by TF-DNA binding assays (P2, 1, 3, 4, 6, 7) …………………… WP1.5 Cell-type-specific in vivo footprinting (P3) …………………. # WP2.1: Isolation of orthologous genes (P2, all partners involved) ……………………………………… WP2.2: Computational analysis of promoters from orthologous and paralogous genes (P5, 7) ………………………………… WP3.1: Activity of cis-elements in the homologous species (P7, P1, 2, 3, 4, 6) ………………………………… WP3.2: Activity of regulatory sequences in heterologous species (P6, P1, 2, 3, 4, 7) ………………………………… WP3.3. Complementation of Arabidopsis mutants with orthologous genes (P4, and others) ……………………………………. WP3.4 Isolation of regulatory mutants by TILLING (P3) …………………………………..

D3. Problems and changes in workplan Describe any difficulties and problems that have hindered the achievement of the planned objectives and any changes with respect to the original objectives and the workplan (maximum 1 page).

Describe difficulties and problems encountered

D4. Collaboration, human mobility and training within the consortium - Describe how coordination takes place (coordination meetings, communications, etc.) - Describe the added value accomplished by collaboration among partners of the consortium. Refer explicitly to joint milestones and deliverables produced during the reporting period. - Describe any sharing of facilities within the consortium. - Describe any exchange of researchers and trainees between partners of the consortium.

D5. Other collaborations directly related to the project - Describe the collaborations with other parties than consortium members. - Describe any sharing of facilities with parties other than consortium members. - Describe any exchange of researchers and trainees with other parties than consortium members.

# E. Dissemination

| E1. Project-derived peer-reviewed publications and patents |  |  |  |
| --- | --- | --- | --- |
|  | Reference | Type of publication (peer-reviewed article / patent) | Partners involved (PX, PY,..) |
| 1 |  |  |  |
| 2 |  |  |  |
| 3 |  |  |  |
| 4 |  |  |  |

Create extra rows if needed

| E2. Other dissemination |  |  |  |
| --- | --- | --- | --- |
|  | Reference | Type of publication (poster abstract/ article in non-peer reviewed science journal /article in newspaper / interview / …) | Partners involved (PX, PY,..) |
| 1 |  |  |  |
| 2 |  |  |  |
| 3 |  |  |  |
| 4 |  |  |  |

Create extra rows if needed

# F. Brief financial report

| F1. Expenditures of the granted budgets (months 1-18) |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Person months | Type (postdoc /..) | Personnel costs (€) | Consumables (€) | Travel (€) | Equipment (€) | Total costs (€) |
| P1 |  |  |  |  |  |  |  |
| P2 |  |  |  |  |  |  |  |
| P3 |  |  |  |  |  |  |  |
| Create extra rows if needed |  |  |  |  |  |  |  |
| Total |  |  |  |  |  |  |  |

| F2. Own contributions (months 1-18) |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Person months | Type (postdoc /..) | Personnel costs (€) | Consumables (€) | Travel (€) | Equipment (€) | Total costs (€) |
| P1 |  |  |  |  |  |  |  |
| P2 |  |  |  |  |  |  |  |
| P3 |  |  |  |  |  |  |  |
| Create extra rows if needed |  |  |  |  |  |  |  |
| Total |  |  |  |  |  |  |  |